## Slide 1: Meeting with Oksana
27/03

## Slide 2: Tasks From Last Meeting
Generate dataset with IsaacSIM
Install v2e
Generate plots of prediction in time

## Slide 3: Completed Tasks

## Slide 4: Argmax vs Weighted Average

## Slide 5: Video Plots q4

## Slide 6: Video Plots q4

## Slide 7: Video Plots q8

## Slide 8: Video Plots q8

## Slide 9: Ongoing and Proposed Future Tasks

## Slide 10: Ongoing Tasks
Generating a dataset with IsaacSIM
  Shadow is still present
  Three options
    Keep trying to get rid of it
    Generate videos with the shadows
    Wait 1s between screenshots -> 3s per screenshot
  Problem: too much time (days) for generating a dataset.
    1000 fps -> 3 hours per video (due to the shadow, maybe 1h if I can remove it)
  Solution: frame interpolation (v2e)

## Slide 11: Ongoing Tasks
V2E installation
  I can’t install some of the modules

## Slide 12: Proposed Future Tasks
Experiment with the weighted average in the models
Finish V2E installation
Generate the IsaacSim dataset 10ms with shadow